## Sheet1
Throttle control by Leap Motion | [5 empty] | Experimentation results in a dark environment (100 times)
Fingers | delay(ms) | status |  |  |  | Throttle control |  | UP | DOWN
1 | 50 | stable |  |  |  | SUCCESS |  | 95 | 97
2 | 100 | stable |  |  |  | FAILED |  | 5 | 3
3 | 200 | normal |  |  |  | Success rate |  | 95% | 97%
4 | 400 | normal
5 | 450 | unstable
| Milestones | Task name | SEP | OCT | NOV | Dec | Jan | Feb | Mar | Apr | May | Month
|  | Project first meeting | Month: 09--10
|  | Background research | Month: 09--11
|  | Microcontroller selection | Month: 10--11
|  | Gesture sensor selection | Month: 10
|  | Gesture sensor learn and test | Month: 10--11
|  | Proposal | Month: 09--10
|  | Necessary components selection | Month: 10--12
|  | Drive integrated circuit test | Month: 11--01
|  | Motors test | Month: 12--01
|  | Moderator interview | Month: 10--11
|  | Handheld controller modified and test | Month: 12--01
|  | Sensor-PC-microcontroller connection | Month: 11--01
|  | Christmas Break | Month: 12--02
|  | Hardware construction | Month: 12--02
|  | Communication codes development | Month: 11--03
|  | Hardware and software combination | Month: 02--03
|  | System test without Quadcopter | Month: 03--04
|  | System test with Quadcopter | Month: 04--05
|  | Throttle control successfully | Month: 5
|  | Further work consider | Month: 5
|  | Final thesis | Month: 03--05
|  | Easter break | Month: 03--05
|  | Milestones check | Month: 5
|  | Final thesis deadline | Month: 5
|  | Presentation | Month: 5